## Spring
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Trajectory Analysis of Single-Cell mRNA Sequencing Data
[5 empty] | PHASE ONE | [34 empty] | PHASE TWO | [41 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Team Composition | All | 2022-01-17 | 2022-02-01 | 14 | 2022-03-21 M: Spring Break
Project Proposal
Introduction & Background | Person 1 | 2022-02-02 | 2022-02-13 | 11 | bar: 2022-01-31 W to 2022-02-07 U
Problem Definition | Person 1 | 2022-02-02 | 2022-02-13 | 11 | bar: 2022-01-31 W to 2022-02-07 U
Methods | Person 2 & 3 | 2022-02-02 | 2022-02-13 | 11 | bar: 2022-01-31 W to 2022-02-07 U
Potential Dataset | Person 2 & 3 | 2022-02-02 | 2022-02-13 | 11 | bar: 2022-01-31 W to 2022-02-07 U
Potential Results & Discussion | Person 4 & 5 | 2022-02-02 | 2022-02-13 | 11 | bar: 2022-01-31 W to 2022-02-07 U
Video Creation & Recording | All | 2022-02-10 | 2022-02-17 | 7 | bar: 2022-02-07 R to 2022-02-14 R
GitHub Page | Person 1 | 2022-02-10 | 2022-02-17 | 7 | bar: 2022-02-14 M to 2022-02-14 R
Midterm Report
Model 1 (M1) Design & Selection | Person 1,2 & 3 | 2022-02-17 | 2022-02-27 | 10 | bar: 2022-02-14 F to 2022-02-21 U
M1 Data Cleaning | Person 1 | 2022-02-17 | 2022-02-27 | 10 | bar: 2022-02-14 F to 2022-02-21 U
M1 Data Visualization | Person 2 | 2022-02-17 | 2022-02-27 | 10 | bar: 2022-02-14 F to 2022-02-21 U
M1 Feature Reduction | Person 3 | 2022-02-17 | 2022-02-27 | 10 | bar: 2022-02-14 F to 2022-02-21 U
M1 Implementation & Coding | Person 4 | 2022-02-28 | 2022-03-17 | 17 | bar: 2022-02-28 M to 2022-03-14 R
M1 Results Evaluation | All | 2022-03-18 | 2022-03-20 | 2 | bar: 2022-02-28 M to 2022-02-28 U; 2022-03-14 F to 2022-03-14 U
Model 2 (M2) Design & Selection | Person 1,2 & 3 | 2022-02-28 | 2022-03-06 | 6 | bar: 2022-02-28 M to 2022-02-28 U
M2 Data Cleaning | Person 1 | 2022-02-28 | 2022-03-06 | 6 | bar: 2022-02-28 M to 2022-02-28 U
M2 Data Visualization | Person 2 | 2022-02-28 | 2022-03-06 | 6 | bar: 2022-02-28 M to 2022-02-28 U
M2 Feature Reduction | Person 3 | 2022-02-28 | 2022-03-06 | 6 | bar: 2022-02-28 M to 2022-02-28 U
M2 Coding & Implementation | Person 5 | 2022-03-07 | 2022-03-17 | 10 | bar: 2022-03-07 M to 2022-03-14 R
M2 Results Evaluation | All | 2022-03-18 | 2022-03-20 | 2 | bar: 2022-03-14 F to 2022-03-14 U
Midterm Report | All | 2022-03-28 | 2022-04-05 | 7 | bar: 2022-03-28 M to 2022-04-04 T
Final Report
Model 3 (M3) Design & Selection | Person 1,2 & 3 | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-03-14 M to 2022-03-14 U
M3 Data Cleaning | Person 1 | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-03-14 M to 2022-03-14 U
M3 Data Visualization | Person 2 | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-03-14 M to 2022-03-14 U
M3 Feature Reduction | Person 3 | 2022-03-14 | 2022-03-20 | 6 | bar: 2022-03-14 M to 2022-03-14 U
M3 Implementation & Coding | Person 4 | 2022-04-06 | 2022-04-14 | 8 | bar: 2022-04-04 W to 2022-04-11 R
M3 Results Evaluation | All | 2022-04-15 | 2022-04-17 | 2 | bar: 2022-04-11 F to 2022-04-11 U
M1-M3 Comparison | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-04-18 M to 2022-04-25 T
Video Creation & Recording | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-04-18 M to 2022-04-25 T
Final Report | All | 2022-04-18 | 2022-04-26 | 8 | bar: 2022-04-18 M to 2022-04-25 T

## Fall
GANTT CHART | [21 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Trajectory Analysis of Single-Cell mRNA Sequencing Data
|  | PHASE ONE | [13 empty] | PHASE TWO | [34 empty] | PHASE THREE
TASK TITLE | TASK OWNER | 2021-09-26 | [6 empty] | 2021-10-03 | [6 empty] | 2021-10-10 | [6 empty] | 2021-10-17 | [6 empty] | 2021-10-24 | [6 empty] | 2021-10-31 | [6 empty] | 2021-11-07 | [6 empty] | 2021-11-14 | [6 empty] | 2021-11-21 | [6 empty] | 2021-11-28 | [6 empty] | 2021-12-05
|  | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | Jay | bar: 2021-09-26 M to 2021-09-26 U; 2021-11-28 M to 2021-11-28 U
Problem Definition | Anjana | bar: 2021-09-26 M to 2021-09-26 U; 2021-11-28 M to 2021-11-28 U
Methods | Josh & Nina | bar: 2021-09-26 M to 2021-09-26 U; 2021-11-28 M to 2021-11-28 U
Potential Results & Discussion | Jay, Vishal, & Anjana | bar: 2021-09-26 M to 2021-09-26 U; 2021-11-28 M to 2021-11-28 U
Video Recording | Jay & Vishal | bar: 2021-10-03 M to 2021-10-03 W; 2021-11-28 M to 2021-11-28 U
GitHub Page | Josh & Nina | bar: 2021-10-03 M to 2021-10-03 W; 2021-11-28 M to 2021-11-28 U
Unsupervised Learning
Data Sourcing and Cleaning | Vishal & Jay | bar: 2021-10-03 R to 2021-10-10 R; 2021-11-28 M to 2021-11-28 U
Model Selection | All | bar: 2021-10-10 F to 2021-10-10 U; 2021-11-28 M to 2021-11-28 U
Data Pre-Processing | Vishal & Jay | bar: 2021-11-28 M to 2021-11-28 U
Model Coding | Josh & Nina | bar: 2021-10-24 M to 2021-10-31 U; 2021-11-28 M to 2021-11-28 U
Results Evaluation and Analysis | Jay, Vishal, & Anjana | bar: 2021-11-07 M to 2021-11-14 M; 2021-11-28 M to 2021-11-28 U
Midterm Report | All | bar: 2021-11-07 M to 2021-11-14 M; 2021-11-28 M to 2021-11-28 U
Supervised Learning
Model Selection | All | bar: 2021-10-17 F to 2021-10-17 U; 2021-11-28 M to 2021-11-28 U
Data Pre-Processing | Anjana & Josh | bar: 2021-10-24 M to 2021-10-24 R; 2021-11-28 M to 2021-11-28 U
Model Coding | Josh & Nina | bar: 2021-10-24 F to 2021-10-31 U; 2021-11-14 T to 2021-11-14 R; 2021-11-28 M to 2021-11-28 U
Results Evaluation and Analysis | Jay, Vishal, & Anjana | bar: 2021-11-14 F to 2021-11-21 T; 2021-11-28 M to 2021-11-28 U
Evaluation
Model Comparison | All | bar: 2021-11-28 M to 2021-12-05 M
Presentation | All | bar: 2021-11-28 M to 2021-11-28 U
Recording | All | bar: 2021-11-28 M to 2021-11-28 U
Website | Josh | bar: 2021-11-28 M to 2021-11-28 U
Video Editing | Jay, Vishal, Nina & Anjana | bar: 2021-11-28 M to 2021-11-28 U
Final Report | All | bar: 2021-11-28 M to 2021-12-05 M

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | NHL Playoff Predictor
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | 2021-10-04 | 2021-10-11 |  | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06
Project Proposal |  | 2021-09-27 | 2021-10-07 | 10
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2021-10-07 | 2021-11-16 | 39
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2021-11-24 | 2021-12-07 | 13
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8