## Sheet1
| Josh | Anjana | Vishal | Nina | Jay
Sept 1 - Oct 7 | Proposal | Lit Review, Proposal | Lit Review, Proposal | Proposal | Lit Review, Proposal
Oct 7: Proposal Due | - | - | - | - | -
Oct 7 - 15 | Unsupervised EDA | Data Pre-Processing | Data Pre-Processing | Unsupervised EDA | Data Pre-Processing
Oct 15 - 31 | Unsupervised Subproject Code | Unsupervised Subproject Eval | Unsupervised Subproject Viz | Unsupervised Subproject Code | Unsupervised Subproject Eval
Nov 1 - 11 | Midterm Report (Methods) | Midterm Report (Problem Definition) | Midterm Report (Results) | Midterm Report (Data Collection + Discussion) | Midterm Report (Intro/ Background)
Nov 11: Midterm Report | - | - | - | - | -
Nov 11 - 21 | Supervised Subproject Code | Supervised Subproject Baseline | Supervised Subproject Eval | Supervised Subproject Code | Supervised Subproject Viz
Nov 21 - Dec 1 | Final report (Viz + Data Collection) | Final Report (Introduction/Background) | Final Report (Methods + Problem Definition) | Final Report (Conclusion) | Final Report (Results)
Dec 1 - Dec 6 | Website | Video Editing | Video Script + Visuals | Video Script + Visuals | Video Recording
Dec 6: Final Project Due | - | - | - | - | -